## Dashboard
AFRICA'S EDTECH BREAKTHROUGH PROJECT
Integrated Financial Model — 7 Programme Years from Programme Start Date
KEY METRICS
Total DP Ask ($M)
Project Duration
Sun-Project V&P_Core ($M)
Planet-Projects ($M)
Ecosystem Fund DP Bridge ($M)
SpoDit Revenue at Maturity ($M/yr)
Platform OpEx at Maturity ($M/yr)
Total Cost per Pilot Country ($M)
Total Cost per Learner at Maturity ($)
SpoDit Sensitivity Factor
FUNDING TRANCHES
| Period | V&P_Core ($M) | Planets ($M) | Eco Fund ($M) | Total ($M)
Tranche 1: Establish & Early Scale | Y1–Y2
Tranche 2: Acceleration | Y3–Y4
Tranche 3: Maturity & Transition | Y5–Y7
TOTAL
ANNUAL DP FUNDING PROFILE ($M)
Component | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
V&P_Core (Sun)
Planet-Projects
Ecosystem Fund DP Bridge
Total DP Funding
Cumulative DP Funding
Calendar Year (approx)
SUSTAINABILITY TRANSITION
Self-Funded % (Earned / Total Revenue)
SpoDit Revenue ($M)
Trademark Revenue ($M)
Net Surplus / (Deficit) ($M)
TRANCHE DECISION GATES — from The Ask, Section 9
Tranche 1 → 2 Gate (end Y2) |  | Platform readiness, institutional formation (incl. GEOS), early adoption in pilot countries, delivery capacity, Stakeholder Alignment momentum.
Tranche 2 → 3 Gate (end Y4) |  | Accelerating adoption, ecosystem depth, operational use of outcome assurance, revenue framework validated (revenue ramp begins Y3), SpoDit viability confirmed.
Tranche 3 Exit (end Y7) |  | Transition to self-funding confirmed, institutional hand-offs complete, clean sunset of time-bounded coordination.
Scenario Levers →
SpoDit Sensitivity Factor (Assumptions B29)
Funded Tranches Toggle (Assumptions B30)
Change these values to run what-if scenarios. Results update across all sheets automatically.

## Assumptions
ASSUMPTIONS & PARAMETERS
Blue = hardcoded input ¦ Black = formula ¦ Green = cross-sheet link ¦ Yellow background = key scenario lever
General Parameters
Programme Start Date | 2026-10-01 | Source: To be confirmed. Default Q4 2026.
Programme End Date (derived) |  | 7 years from Programme Start Date
Project duration (programme years) | 7 | Source: The Ask (Essay 27)
Currency | USD
Units | Millions ($M)
Pilot countries (Phase 1) | 6 | Source: The Ask, Section 1
Target countries at maturity | 44 | At least 80% of AU Member States (44 countries)
Estimated learner population at maturity (M) | 200 | Source: Essay series; conservative estimate of RESPECT-reached learners at programme maturity (Y7)
Tranche Structure ($M) — from The Ask, Section 9
Tranche 1: Establish & Early Scale (Y1–Y2) | 129.6
Tranche 2: Acceleration (Y3–Y4) | 168.6
Tranche 3: Maturity & Transition (Y5–Y7) | 188
Total (Tranche presentation figures)
Note: Tranche figures ($486.2M) now match the annual detail sum. The Canon grand total ($488.2M)
uses ceiling-rounded V&P_Core ($173M vs $171M annual sum); the $2M rounding gap is documented.
PP budgets include a 7% coordination levy funding the AUDA-NEPAD EdTech Task Force (Essay 27).
Platform & Revenue Maturity Targets
Platform OpEx at maturity ($M/yr) | 25 | Source: The Ask Section 2; comparable to Moodle ~$24M, DHIS2 ~$23M, Open edX ~$25–30M
Trademark rev self-funding year | Y7 | Source: The Ask, Section 6
SpoDit revenue at maturity ($M/yr) | 200 | Source: SpoDits Essay (Essay 9), Section 6
SpoDit full takeover year | Y7 | Source: SpoDits Essay, Section 6
SpoDit Revenue Sensitivity Factor | 100% | Set to 100% for base case. Change to test scenarios (e.g., 50% = SpoDits reach half of target).
Funded Tranches (1, 2, or 3) | 3 | Set to 3 for base case (all tranches). Set to 1 or 2 to model partial funding scenarios.
SpoDit Revenue Ramp ($M) — from SpoDits Essay, Section 6
| Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
SpoDit Revenue (base case) | 0 | 0 | 5 | 20 | 60 | 130 | 200
SpoDit Revenue (scenario-adjusted)
Ecosystem Fund DP Bridge | 5 | 10 | 20 | 35 | 50 | 60 | 0
Total Ecosystem Funding (SpoDit + DP)
Platform Trademark & Certification Revenue Ramp ($M)
| Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
Trademark & Certification Revenue | 0 | 0 | 0.5 | 2.5 | 8 | 17 | 25
Note: Revenue ramps follow an S-curve from zero (Tranche 1) to target values at Y7. No revenue in Y1–Y2 (pilot scale insufficient).
V&P_Core Annual Targets ($M) — from The Ask (Essay 27), Table 1
| Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
V&P_Core (The Ask Table 1) | 25 | 29 | 33.5 | 35.5 | 26 | 16 | 6
Key Model Notes
• Programme years Y1–Y7 are full 12-month periods starting from the Programme Start Date.
• Annual phasing of Planet-Projects: levied values (×1.07) from The Ask Table 2 (Essay 27), plus EdTech Task Force PP.
• V&P_Core annual targets: exact values from The Ask Table 1 (Essay 27).
• V&P_Core workstream distribution: estimated profiles constrained by workstream budgets.
• Workstream totals ($180.55M) from V&P_Core Project Plan exceed The Ask sum ($171M); variance of $9.55M flagged.
• SpoDit revenue ramp: from SpoDits Essay (Essay 9), Section 6.
• Ecosystem Fund DP Bridge: from SpoDits Essay and The Ask Table 1.
• Platform OpEx maturity benchmark: Moodle HQ ~$24M, DHIS2/HISP ~$23M, Open edX ~$20M.
• Three-Pillar Governance: AUDA-NEPAD (Political), Fiduciary Trustee TBD, Spix Foundation (Technical).
Note on B12: Conservative estimate: ~200M learners reached by RESPECT at maturity (2032). Africa has ~350M school-age children (K-12). Assumes ~57% RESPECT penetration across 55 AU member states by end of Phase 3. This is a scenario-testable input — change it to see the effect on cost-per-learner on the Dashboard.
Note on C40: Assumption: ramp from $0 to $25M based on The Ask Section 2 & 6. Profile is an estimate; annual values are scenario-testable inputs.
Note on B41: The Ask Section 2 states platform OpEx at maturity is ~$25M/yr. Section 6 states trademark revenue reaches self-funding by 2032. No source table provides year-by-year trademark revenue. These values are scenario-testable inputs (yellow cells) that a reviewer can adjust.

## Sources of Funds
SOURCES OF FUNDS — DEVELOPMENT PARTNER FUNDING
USD Millions — From The Ask (Essay 27), Tables 1 & 2. PP budgets include 7% coordination levy.
Component | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
DP Funding by Major Component ($M)
V&P_Core (Sun-Project)
Planet-Projects (Total) | 29.4 | 31.2 | 27.1 | 17.5 | 11.6 | 9.5 | 8.9
Ecosystem Fund DP Bridge
TOTAL DP FUNDING
Cumulative DP Funding
DP Funding as % of Annual Total
V&P_Core (Sun-Project)
Planet-Projects (Total)
Ecosystem Fund DP Bridge
Tranche Allocation ($M) — computed from annual detail
Tranche 1 (Y1–Y2)
Tranche 2 (Y3–Y4)
Tranche 3 (Y5–Y7)
Total (computed)
vs Assumptions tranche total |  | Difference reflects rounding between presentation-level and detail-level figures in The Ask
TRANCHE-ADJUSTED DP FUNDING ($M) — reflects Funded Tranches toggle on Assumptions
Component | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
Tranche-Adjusted Total DP
Cumulative (Tranche-Adjusted)
Funding Gap vs Full Ask
Note: The tranche toggle zeros out DP inflows for unfunded tranches but does not reduce expenditure.
This is intentional: it shows the funding gap, which is what a Development Partner needs to see.
A "Tranche 1 only" scenario means $124.9M funded against the full cost plan — the gap quantifies what remains unfunded.

## V&P_Core Detail
V&P_CORE (SUN-PROJECT) — WORKSTREAM DETAIL
USD Millions — ~$181M workstream planning estimates over 7 years (Canon Ask: $171M annual sum / $173M ceiling-rounded)
Workstream | Budget ($M) | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Sum (Check)
Platform Development (DP Bridge) | 91 | 12 | 15 | 18 | 20 | 15 | 11 | 0
Stakeholder Alignment Programs (SAPs) | 35 | 7 | 7 | 6 | 5 | 4 | 4 | 2
AUDA-NEPAD EdTech Task Force | 15 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 1
Pilot Deployment (6 countries) | 10 | 3 | 3.5 | 2 | 1 | 0.5 | 0 | 0
Scaling Operations | 9 | 0 | 0 | 1.5 | 2.5 | 2.5 | 2 | 0.5
Spix Foundation Operations | 8.5 | 0.7 | 0.9 | 1.2 | 1.5 | 1.5 | 1.5 | 1.2
Contingency | 5 | 0.5 | 0.5 | 0.7 | 0.8 | 0.8 | 0.8 | 0.9
Institutional Incubation | 2.75 | 0.1 | 0.15 | 0.4 | 0.5 | 0.6 | 0.5 | 0.5
Governance & Fiduciary | 2.5 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3
Fundraising & DP Relations | 1.8 | 0.4 | 0.4 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1
TOTAL V&P_CORE
The Ask annual targets
Variance (model vs Ask)
Phase Summary ($M)
Phase 1: Prove (Y1–Y2)
Phase 2: Scale (Y3–Y4)
Phase 3: Sustain (Y5–Y7)
Note on A17: Variance arises because V&P_Core Project Plan workstream totals ($180.55M) differ from The Ask Table 1 annual sum ($179.7M) by $0.85M — a rounding gap between two source documents. The workstream profiles are distributional estimates; The Ask annual totals are authoritative.

## Planet-Projects Detail
PLANET-PROJECTS — ANNUAL DETAIL
USD Millions — From The Ask (Essay 27), Table 2. Original PP budgets include 7% coordination levy.
Planet-Project | Duration | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
ECM | 4 years | 2.7 | 2.7 | 2.7 | 2.7 | 0 | 0 | 0
Easy FLN Localization | 4 years | 2.1 | 2.7 | 2.1 | 1.6 | 0 | 0 | 0
RBF4Ed | 7 years | 4.3 | 4.3 | 3.7 | 3.2 | 3.2 | 2.7 | 2.1
IMPACT Board | 7 years | 2.7 | 2.7 | 2.1 | 2.1 | 2.1 | 1.6 | 1.6
PREMIER Institute | 7 years | 3.2 | 3.2 | 5.9 | 5.9 | 4.3 | 3.2 | 3.2
CRADLE | 2 years | 5.4 | 5.4 | 0 | 0 | 0 | 0 | 0
PROMISE | 3 years | 3.7 | 3.2 | 2.7 | 0 | 0 | 0 | 0
SLATE | 3 years | 3.2 | 4.3 | 3.2 | 0 | 0 | 0 | 0
BEINGS | 3 years | 2.1 | 2.7 | 2.7 | 0 | 0 | 0 | 0
AUDA-NEPAD EdTech Task Force | 5 years | 0 | 0 | 2 | 2 | 2 | 2 | 2
TOTAL PLANET-PROJECTS
Cross-check vs Sources of Funds
Natural Development Partner Profiles & Legacy Attribution
ECM | Gates Foundation |  | Legacy: "The ECM, Founded by [DP]"
Easy FLN Localization | Research-focused DPs |  | Legacy: "The Easy FLN Localization, Founded by [DP]"
RBF4Ed | IFFEd, GPE, Gates Foundation |  | Legacy: "The RBF4Ed, Founded by [DP]"
IMPACT Board | Luqmān Project |  | Legacy: "The IMPACT Board, Founded by [DP]"
PREMIER Institute | Research-focused DPs |  | Legacy: "The PREMIER Institute, Founded by [DP]"
CRADLE | DPI/data governance DPs |  | Legacy: "The CRADLE, Founded by [DP]"
PROMISE | Bilateral donors (teacher dev) |  | Legacy: "The PROMISE, Founded by [DP]"
SLATE | Chinese development agencies |  | Legacy: "The SLATE, Founded by [DP]"
BEINGS | European GovStack DPs (GIZ, EU, Finland, Estonia) |  | Legacy: "The BEINGS, Founded by [DP]"
AUDA-NEPAD EdTech Task Force | EU (anticipated) |  | Legacy: "The AUDA-NEPAD EdTech Task Force, Founded by [DP]"

## Revenue & Sustainability
REVENUE & SUSTAINABILITY TRANSITION
USD Millions — All earned revenue flows through the SpoDit sensitivity factor on the Assumptions sheet
Revenue Stream | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total / Maturity
RESPECT Ecosystem Revenue ($M)
Sponsor Credit (SpoDit) Revenue
Ecosystem Fund DP Bridge
Total Ecosystem Funding
SpoDit % of Ecosystem Funding
RESPECT Platform Revenue ($M)
Trademark & Certification Revenue
Platform DP Bridge (within V&P_Core)
Total Platform Funding
Trademark % of Platform Funding
Consolidated Revenue Summary ($M)
Total DP Funding (all sources)
SpoDit Revenue
Trademark & Certification Revenue
TOTAL REVENUE
Self-Funded % (Earned / Total Revenue)
POST-PROGRAMME SUSTAINABILITY MEMO
Revenue Stream | Sustainability Mechanism | At Maturity ($M/yr)
RESPECT Platform | Self-funding via trademark licensing and certification revenue (~$25M/yr at maturity).
RESPECT Ecosystem | Self-funding via Sponsor Credits (SpoDits) (~$200M/yr at maturity).
GEOS Organization (from RBF4Ed) | Designed to become self-funding via GEOSor examination and certification fees. | TBD
IMPACT Board | Designed to become self-funding via professional certification fees (Mappers, Impletors, DiPians). | TBD
SOCLE Board (from ECM) | Designed to become self-funding via curriculum standard maintenance fees. | TBD

## Statement of Activities
CONSOLIDATED STATEMENT OF ACTIVITIES
USD Millions — "Revenue" = DP grants + earned income; "Expenditure" = program costs
Line Item | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
REVENUE / SUPPORT
DP Grants — V&P_Core
DP Grants — Planet-Projects
DP Grants — Ecosystem Fund Bridge
Sponsor Credit (SpoDit) Revenue
Trademark & Certification Revenue
TOTAL REVENUE
EXPENDITURE / PROGRAM COSTS
V&P_Core Program Costs
Planet-Projects Program Costs
Ecosystem Fund Disbursements (to AppDevs/Localizers)
TOTAL EXPENDITURE
NET POSITION
Net Surplus / (Deficit)
MEMO: Revenue Composition
DP Grants as % of Revenue
Earned Revenue as % of Revenue

## Cash Flow
CASH FLOW STATEMENT
USD Millions — Sources, uses, and net cash position by year
Line Item | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Total
CASH INFLOWS
DP Tranche Disbursements
SpoDit Revenue
Trademark & Certification Revenue
TOTAL CASH INFLOWS
CASH OUTFLOWS
V&P_Core Operations
Planet-Projects Operations
Ecosystem Fund Disbursements
TOTAL CASH OUTFLOWS
NET CASH POSITION
Net Cash Flow (Inflows − Outflows)
Opening Cash Balance | 0
Closing Cash Balance
CASH FLOW PRIORITY NOTES
In a constrained funding scenario, cash allocation follows this priority:
1. Platform Operations — maintaining the RESPECT Platform is existential; without it, all else stops.
2. Governance & Fiduciary — legal, audit, and trustee obligations are non-discretionary.
3. Pilot Country Deployment — contractual commitments to Ministries of Education in 6 pilot countries.
4. Planet-Project Operations — ongoing research and institutional commitments (staff, university partners).
5. Ecosystem Fund Disbursements — payments to AppDevs/Localizers, scalable to available funds.
6. Scaling Operations & Contingency — discretionary expansion, deferrable without system damage.
This priority order is a governance principle, not a formula. Actual allocation follows fiduciary trustee decisions.

## Charts
VISUALIZATIONS
Charts derived from model data — for board presentations and DP briefings
Programme Year | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7
DP Grants ($M)
SpoDit Revenue ($M)
Trademark Revenue ($M)
Self-Funded %
V&P_Core ($M)
Planet-Projects ($M)
Ecosystem Fund ($M)
Net Surplus / (Deficit) ($M)